## Project_plan
Section | Topic | Detail | Phase (indicative) | Notes / owner
Phases | A — Foundation | Vault/secrets, CI/CD, env promotion, structured logs + metrics + tracing, SSO + RBAC baseline.API availability | 4–8 wk | Eng + Security
Phases | B — Mailbox MVP | Connector (poll/subscribe), queue to pipeline workers, non-prod Nomura mailboxes, UAT path prep | 8–14 wk | Eng + Platform
Phases | C — Booking & SSI | Replace CSV with read APIs/feeds for BO→MO→FO (or agreed order); | 10–16 wk | Overlap B | here csv is the source data files , assumption is initial dev will happen with stubbed API calls with data coming from csv and lateron API integration will happen
Phases | D — Pilot | Pilot with limited users, KPIs measure (latency, precision/recall sample, Ai analysis accuracy) | 4–6 wk | Ops + Eng
Nomura mailbox | Discovery | Understanding requirement , Which shared mailboxes/data sources in v1; | A–B | Ops + Sec
Nomura mailbox | Threading | Align Message-ID, In-Reply-To, References, conversation IDs to internal case; define 'latest reply' vs full thread for classifier. | B
Nomura mailbox | Non-functional | API rate limits, attachment size limits, malware scan before extract, PII handling for third-party LLM. | B | Sec
Internal systems | Murex (or primary book) | Match logic | C | Protiviti
Internal systems | BO / MO / FO | Match logic , Read-only integration first; preserve business rule BO→MO→FO stop-at-first-hit if still mandated. | C | Protiviti
Internal systems | static data | tools, agents, instructions for mismatch reasons and drafter context. | C | Protiviti
Internal systems | DTCC / MarkitWire / SWIFT | Clarify whether pipeline reads only from Murex/hub vs multiple hops; reduce duplicate truth. | C | Architecture
Internal systems | Identity management | integrate with SSO | A | Identity management
Internal systems | Admin role | role mapping in admin portal and admin access portal definition | A
Internal systems | Audit | Append-only store; link user id, case id, message id for regulatory samples. | A–D
Internal systems | Ticketing (optional) | ServiceNow/Jira webhook from Escalate actions for FO/SSI workflows. | A–D
LLM governance | Hosting | Cloud API vs on-prem / Hugging Face endpoints — network zone, latency, data residency. | A–C | Sec + Eng
LLM governance | Controls | Prompt versioning, PII scrubbing, JSON schema validation on outputs, low-confidence surfacing in UI. | A–D
LLM governance | Fallback | Rules-only classifier/extract path when LLM disabled or unhealthy (align with prototype rules path). | All
Risks | Mail API throttling | Mitigation: webhook or batched approach | B
Risks | Field drift | Mitigation: versioned contracts with Murex/feeds; automated contract tests on release. | C
Risks | LLM extract errors | Mitigation: schema validation, human review band, confidence thresholds. | B–D
Risks | Scope creep | Mitigation: vertical slice — one product, one desk, one mailbox before broad rollout. | All | Nomura