## AI Ops POC Plan
# | Category | Sub-Category | Task | Responsibility | SPOC | Status | Comments
1 | DISCOVERY & REQUIREMENTS | Use Case Scoping | Document all Allege exception use cases for OTC Derivatives asset class | Nomura | Sandhya | 50% done
2 | DISCOVERY & REQUIREMENTS | Use Case Scoping | Document all Allege exception use cases for FX asset class | Nomura | Sandhya | Not started
3 | DISCOVERY & REQUIREMENTS | Use Case Scoping | Prioritise use cases for POC scope with business sign-off | Nomura |  | Done
4 | DISCOVERY & REQUIREMENTS | Use Case Scoping | Map each use case to input source: Email / TRAM / Shared Folder | Nomura | Sandhya | Not started
5 | DISCOVERY & REQUIREMENTS | Use Case Scoping | Define expected output / resolution action per use case | Nomura | Sandhya
6 | DISCOVERY & REQUIREMENTS | Use Case Scoping | Define action update requirements in downstream systems (e.g. Phoenix Cash Manager, Settlement, MO, BO systems) | Nomura | Sandhya | Not started
7 | DISCOVERY & REQUIREMENTS | BRD & Tech Handover | Finalise and version-lock BRD document | Nomura | Sandhya |  | I'm adding SIPOC as part of BRD , should we add it as separate line item so that we don't forget it?
8 | DISCOVERY & REQUIREMENTS | BRD & Tech Handover | Prepare SIPOC for OTC derivative and FX asset class POC | Nomura | Sandhya
9 | DISCOVERY & REQUIREMENTS | BRD & Tech Handover | Prepare highlevel technical specification document (architecture, APIs, data flows) | Nomura | Gopi
10 | DISCOVERY & REQUIREMENTS | BRD & Tech Handover | Walk vendor team through BRD, prototype and architecture | Both | Sandhya |  | Is prototype walkthrough needed?
11 | DISCOVERY & REQUIREMENTS | BRD & Tech Handover | Conduct Q&A session with vendor team post-walkthrough | Both
12 | DISCOVERY & REQUIREMENTS | BRD & Tech Handover | Vendor to submit understanding document / solution approach | Vendor
13 | DISCOVERY & REQUIREMENTS | BRD & Tech Handover | Review and sign off vendor solution approach | Nomura
14 | DISCOVERY & REQUIREMENTS | Input Source Requirements | Define email ingestion requirements (mailbox access, parsing rules, attachments) | Nomura
15 | DISCOVERY & REQUIREMENTS | Input Source Requirements | Define TRAM message ingestion requirements (message format, frequency, fields) | Nomura
16 | DISCOVERY & REQUIREMENTS | Input Source Requirements | Define shared folder ingestion requirements (path, file types, polling frequency) | Nomura
17 | DISCOVERY & REQUIREMENTS | Input Source Requirements | Define data classification and routing rules across all 3 input sources | Nomura | Sandhya
18 | DISCOVERY & REQUIREMENTS | Input Source Requirements | Sign off input source requirements with operations team | Nomura | Sandhya
19 | DISCOVERY & REQUIREMENTS | Role Based Access — Requirements | Identify all user roles (Ops analyst, Team Lead, Manager, Compliance, Read-only) | Nomura | Sandhya
20 | DISCOVERY & REQUIREMENTS | Role Based Access — Requirements | Define access permissions per role (view / action / approve / admin) | Nomura | Sandhya
21 | DISCOVERY & REQUIREMENTS | Role Based Access — Requirements | Map RBAC requirements to Nomura IAM / AD standards | Nomura
22 | DISCOVERY & REQUIREMENTS | Role Based Access — Requirements | Document RBAC spec and include in BRD / tech spec | Nomura
23 | DISCOVERY & REQUIREMENTS | Environment Setup — Planning | Confirm vendor sandbox environment specs and access approach | Both
24 | DISCOVERY & REQUIREMENTS | Environment Setup — Planning | Confirm Nomura internal dev environment specs (Chinou / AWS Bedrock) | Nomura
25 | DISCOVERY & REQUIREMENTS | Environment Setup — Planning | Define data masking / anonymisation approach for POC test data | Nomura |  |  | we will give access to actual APIs to vendor?
26 | DISCOVERY & REQUIREMENTS | Environment Setup — Planning | Define data for POC test data | Nomura | Sandhya
27 | DISCOVERY & REQUIREMENTS | Environment Setup — Planning | Agree on integration points between vendor environment and Nomura systems (if any during POC) | Both
28 | DEVELOPMENT — VENDOR | Environment Setup | Set up vendor sandbox / dev environment | Vendor
29 | DEVELOPMENT — VENDOR | Environment Setup | Configure LLM / AI model access in vendor environment | Vendor
30 | DEVELOPMENT — VENDOR | Environment Setup | Set up CI/CD pipeline in vendor environment | Vendor
31 | DEVELOPMENT — VENDOR | Environment Setup | Confirm test data availability and loading in vendor environment | Both
32 | DEVELOPMENT — VENDOR | Iterative Code Handover to Nomura | Agree code handover cadence and schedule with Nomura dev team (sprint/milestone-based) | Both
33 | DEVELOPMENT — VENDOR | Iterative Code Handover to Nomura | Set up shared code repository accessible to both vendor and Nomura dev team | Both
34 | DEVELOPMENT — VENDOR | Iterative Code Handover to Nomura | Handover 1: Push Sprint 1 code to shared repo with release notes | Vendor |  |  | The number of sprints will be dependent on the vendors planning
35 | DEVELOPMENT — VENDOR | Iterative Code Handover to Nomura | Handover 2: Push Sprint 2 code to shared repo with release notes | Vendor
36 | DEVELOPMENT — VENDOR | Iterative Code Handover to Nomura | Handover 3: Push Sprint 3 code to shared repo with release notes | Vendor
37 | DEVELOPMENT — VENDOR | Iterative Code Handover to Nomura | Handover 4: Push final code to shared repo with release notes | Vendor
38 | DEVELOPMENT — VENDOR | Input Source Integration — Email | Build email ingestion connector (mailbox polling / webhook) | Vendor
39 | DEVELOPMENT — VENDOR | Input Source Integration — Email | Implement email parsing and field extraction logic | Vendor
40 | DEVELOPMENT — VENDOR | Input Source Integration — Email | Handle email attachments (PDF, Excel) extraction | Vendor
41 | DEVELOPMENT — VENDOR | Input Source Integration — Email | Unit test email ingestion with sample Nomura data | Vendor
42 | DEVELOPMENT — VENDOR | Input Source Integration — TRAM | Build TRAM message ingestion connector | Vendor
43 | DEVELOPMENT — VENDOR | Input Source Integration — TRAM | Implement TRAM message parsing and structured data extraction | Vendor
44 | DEVELOPMENT — VENDOR | Input Source Integration — TRAM | Handle TRAM message routing to correct use case handler | Vendor
45 | DEVELOPMENT — VENDOR | Input Source Integration — TRAM | Unit test TRAM ingestion with sample messages | Vendor
46 | DEVELOPMENT — VENDOR | Input Source Integration — Shared Folder | Build shared folder service | Vendor
47 | DEVELOPMENT — VENDOR | Input Source Integration — Shared Folder | Implement file type detection and extraction logic | Vendor
48 | DEVELOPMENT — VENDOR | Input Source Integration — Shared Folder | Handle file deduplication and reprocessing controls | Vendor
49 | DEVELOPMENT — VENDOR | Input Source Integration — Shared Folder | Unit test shared folder ingestion with sample files | Vendor
50 | DEVELOPMENT — VENDOR | Core AI Engine — OTC Derivatives | Build AI reasoning / classification layer for OTC Derivatives Allege exceptions | Vendor
51 | DEVELOPMENT — VENDOR | Core AI Engine — OTC Derivatives | Implement RAG or prompt chain for OTC exception resolution suggestions | Vendor
52 | DEVELOPMENT — VENDOR | Core AI Engine — OTC Derivatives | Integrate OTC use case logic with all 3 input sources | Vendor
53 | DEVELOPMENT — VENDOR | Core AI Engine — OTC Derivatives | Implement confidence scoring and fallback to human review | Vendor
54 | DEVELOPMENT — VENDOR | Core AI Engine — OTC Derivatives | Unit test OTC AI engine with representative test cases | Vendor
55 | DEVELOPMENT — VENDOR | Core AI Engine — FX | Build AI reasoning / classification layer for FX Allege exceptions | Vendor
56 | DEVELOPMENT — VENDOR | Core AI Engine — FX | Implement RAG or prompt chain for FX exception resolution suggestions | Vendor
57 | DEVELOPMENT — VENDOR | Core AI Engine — FX | Integrate FX use case logic with all 3 input sources | Vendor
58 | DEVELOPMENT — VENDOR | Core AI Engine — FX | Implement confidence scoring and fallback to human review for FX | Vendor
59 | DEVELOPMENT — VENDOR | Core AI Engine — FX | Unit test FX AI engine with representative test cases | Vendor
60 | DEVELOPMENT — VENDOR | Portal UI Development | Build case queue dashboard (list of exceptions, status, source) | Vendor
61 | DEVELOPMENT — VENDOR | Portal UI Development | Build exception detail view (AI suggestion, evidence, input data) | Vendor
62 | DEVELOPMENT — VENDOR | Portal UI Development | Build action panel (approve / reject / escalate AI suggestion) | Vendor
63 | DEVELOPMENT — VENDOR | Portal UI Development | Build audit trail / activity log view per case | Vendor
64 | DEVELOPMENT — VENDOR | Portal UI Development | Build management summary / metrics dashboard | Vendor
65 | DEVELOPMENT — VENDOR | Portal UI Development | Implement asset class filter (OTC / FX toggle) | Vendor
66 | DEVELOPMENT — VENDOR | Role Based Access Control — Build | Implement RBAC framework in vendor environment | Vendor
67 | DEVELOPMENT — VENDOR | Role Based Access Control — Build | Configure role-to-permission mapping per Nomura RBAC spec | Vendor
68 | DEVELOPMENT — VENDOR | Role Based Access Control — Build | Implement login and session management | Vendor
69 | DEVELOPMENT — VENDOR | Role Based Access Control — Build | Implement UI element visibility control per role | Vendor
70 | DEVELOPMENT — VENDOR | Role Based Access Control — Build | Unit test RBAC — verify each role sees only permitted views and actions | Vendor
71 | DEVELOPMENT — VENDOR | Integration & System Testing — Vendor | End-to-end integration test: Email → AI Engine → Portal UI | Vendor
72 | DEVELOPMENT — VENDOR | Integration & System Testing — Vendor | End-to-end integration test: TRAM → AI Engine → Portal UI | Vendor
73 | DEVELOPMENT — VENDOR | Integration & System Testing — Vendor | End-to-end integration test: Shared Folder → AI Engine → Portal UI | Vendor
74 | DEVELOPMENT — VENDOR | Integration & System Testing — Vendor | Performance and load testing in vendor environment | Vendor
75 | DEVELOPMENT — VENDOR | Integration & System Testing — Vendor | Bug fixes and stabilisation post integration testing | Vendor
76 | DEVELOPMENT — VENDOR | Integration & System Testing — Vendor | Vendor sign-off on dev completion and readiness for Nomura UAT | Vendor
77 | DEVELOPMENT — NOMURA INTERNAL | Environment Setup — Nomura | Provision Nomura internal dev environment on Ops Server | Nomura
78 | DEVELOPMENT — NOMURA INTERNAL | Environment Setup — Nomura | Configure LLM model access | Nomura |  |  | This access is via Chinou ?
79 | DEVELOPMENT — NOMURA INTERNAL | Environment Setup — Nomura | Set up internal code repository and access controls | Nomura
80 | DEVELOPMENT — NOMURA INTERNAL | Environment Setup — Nomura | Confirm NTI approval for Nomura internal dev environment usage | Nomura |  |  | which all approvals or Ids do we need to raise here - automation registry id , NTI id and?
81 | DEVELOPMENT — NOMURA INTERNAL | Environment Setup — Nomura | Raise Automation CoE Registry ID for POC | Nomura
82 | DEVELOPMENT — NOMURA INTERNAL | Environment Setup — Nomura | Raise JIRA ID for POC development tracking | Nomura
83 | DEVELOPMENT — NOMURA INTERNAL | Iterative Code Replication | Pull Sprint 1 code from shared repo and replicate in Nomura environment | Nomura |  |  | will need to define at what intervals Vendor will give the code to Nomura dev team and those many such line items will have to be added.
84 | DEVELOPMENT — NOMURA INTERNAL | Iterative Code Replication | Pull Sprint 2 code from shared repo and replicate in Nomura environment | Nomura |  |  | will need to define at what intervals Vendor will give the code to Nomura dev team and those many such line items will have to be added.
85 | DEVELOPMENT — NOMURA INTERNAL | Iterative Code Replication | Pull Sprint 3 code from shared repo and replicate in Nomura environment | Nomura |  |  | will need to define at what intervals Vendor will give the code to Nomura dev team and those many such line items will have to be added.
86 | DEVELOPMENT — NOMURA INTERNAL | Iterative Code Replication | Pull final code from shared repo and replicate in Nomura environment | Nomura |  |  | will need to define at what intervals Vendor will give the code to Nomura dev team and those many such line items will have to be added.
88 | DEVELOPMENT — NOMURA INTERNAL | Code Replication — OTC Derivatives | Replicate POC codebase in Nomura internal environment | Nomura
90 | DEVELOPMENT — NOMURA INTERNAL | Code Replication — OTC Derivatives | Integrate OTC Derivatives use case with Nomura internal data sources | Nomura
91 | DEVELOPMENT — NOMURA INTERNAL | Code Replication — OTC Derivatives | Run OTC test cases in Nomura environment and compare output vs vendor | Nomura
92 | DEVELOPMENT — NOMURA INTERNAL | Code Replication — FX | Build FX use case in Nomura internal environment (not in prototype) | Nomura
93 | DEVELOPMENT — NOMURA INTERNAL | Code Replication — FX | Integrate FX Allege exceptions with Nomura internal data sources | Nomura
94 | DEVELOPMENT — NOMURA INTERNAL | Code Replication — FX | Run FX test cases in Nomura environment | Nomura
95 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Connect PoC code to Settlement System (test environment) | Nomura
96 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Connect PoC code to Middle Office (MO) system (test environment) | Nomura
97 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Connect PoC code to Back Office (BO) system (test environment) | Nomura
98 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Connect PoC code to System 4 (test environment) [placeholder] | Nomura |  |  | replace the placeholder
99 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Connect PoC code to System 5 (test environment) [placeholder] | Nomura |  |  | replace the placeholder
100 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Connect PoC code to System 6 (test environment) [placeholder] | Nomura |  |  | replace the placeholder
101 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Test action update flow: AI suggestion → Settlement system | Nomura
102 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Test action update flow: AI suggestion → MO system | Nomura
103 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Test action update flow: AI suggestion → BO system | Nomura
104 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Test action update flow: AI suggestion → System 4 [placeholder] | Nomura |  |  | replace the placeholder
105 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Test action update flow: AI suggestion → System 5 [placeholder] | Nomura |  |  | replace the placeholder
106 | DEVELOPMENT — NOMURA INTERNAL | System Connectivity — Nomura Internal | Test action update flow: AI suggestion → System 6 [placeholder] | Nomura |  |  | replace the placeholder
107 | DEVELOPMENT — NOMURA INTERNAL | Input Source Integration — Internal | Build or configure email ingestion in Nomura environment (Nomura mailbox) | Nomura
108 | DEVELOPMENT — NOMURA INTERNAL | Input Source Integration — Internal | Build or configure TRAM message feed in Nomura environment | Nomura
109 | DEVELOPMENT — NOMURA INTERNAL | Input Source Integration — Internal | Build or configure shared folder access in Nomura environment | Nomura
110 | DEVELOPMENT — NOMURA INTERNAL | RBAC — Nomura Environment | Implement RBAC in Nomura environment aligned to Nomura AD / IAM | Nomura
111 | DEVELOPMENT — NOMURA INTERNAL | RBAC — Nomura Environment | Test role permissions in Nomura environment across all user roles | Nomura
112 | DEVELOPMENT — NOMURA INTERNAL | Internal Dev Review | Internal code review and security review | Nomura
113 | DEVELOPMENT — NOMURA INTERNAL | Internal Dev Review | Compare Nomura internal build vs vendor build — gap analysis | Both
114 | DEVELOPMENT — NOMURA INTERNAL | Internal Dev Review | Document findings and decision on preferred build path for production | Nomura
115 | CONTROLS & GOVERNANCE | NTI Approvals | Raise NTI request for vendor POC environment access | Nomura
116 | ROLE BASED ACCESS CONTROL | RBAC Implementation — Vendor | Vendor implements RBAC per signed-off permission matrix | Vendor
118 | ROLE BASED ACCESS CONTROL | RBAC Implementation — Nomura | Nomura tests all role-permission combinations in internal environment | Nomura
119 | INPUT SOURCE INTEGRATION | Email Integration | Vendor builds and unit tests email connector | Vendor
120 | INPUT SOURCE INTEGRATION | Email Integration | Nomura builds email connector in internal environment | Nomura
121 | INPUT SOURCE INTEGRATION | TRAM Integration | Vendor builds and unit tests TRAM connector | Vendor
122 | INPUT SOURCE INTEGRATION | TRAM Integration | Nomura builds TRAM connector in internal environment | Nomura
123 | CONTROLS & GOVERNANCE | NTI Approvals | Raise NTI request for input source connectors (email, TRAM, shared folder) | Nomura
124 | CONTROLS & GOVERNANCE | NTI Approvals | Raise NTI request for system connectivity (Settlement, MO, BO, System4-6) | Nomura |  |  | mention placeholder systems
125 | CONTROLS & GOVERNANCE | NTI Approvals | Track NTI approval status and follow up with CDO / Controls | Nomura
126 | CONTROLS & GOVERNANCE | NTI Approvals | Obtain NTI sign-off before UAT commencement | Nomura
127 | CONTROLS & GOVERNANCE | AI Governance | Register POC in Nomura AI governance forum / Automation CoE / Jira | Nomura
128 | CONTROLS & GOVERNANCE | AI Governance | Raise Automation CoE Registry ID and obtain approval | Nomura
130 | CONTROLS & GOVERNANCE | AI Governance | Prepare AI risk assessment for the POC (model risk, data risk, operational risk) | Nomura
131 | CONTROLS & GOVERNANCE | AI Governance | Review AI governance checklist compliance | Nomura
132 | CONTROLS & GOVERNANCE | AI Governance | Present POC to AI governance forum for review and approval | Nomura
133 | CONTROLS & GOVERNANCE | AI Governance | Incorporate AI governance feedback into POC design | Both
134 | CONTROLS & GOVERNANCE | Data Governance | Identify all data sources used in POC and classify (PII, confidential, public) | Nomura
135 | CONTROLS & GOVERNANCE | Data Governance | Confirm data masking / anonymisation applied to all POC test data | Nomura
136 | CONTROLS & GOVERNANCE | Data Governance | Ensure no live production data used in vendor environment | Nomura
137 | CONTROLS & GOVERNANCE | Data Governance | Data lineage documentation/other documentation for all inputs to AI model | Nomura
138 | CONTROLS & GOVERNANCE | Compliance Review | Review POC against Nomura compliance and regulatory requirements | Nomura
139 | CONTROLS & GOVERNANCE | Compliance Review | Confirm audit trail and logging meets compliance standards | Both
140 | CONTROLS & GOVERNANCE | Compliance Review | Obtain compliance sign-off before UAT | Nomura
141 | CONTROLS & GOVERNANCE | Vendor Controls | Review and sign vendor NDA / data handling agreement | Nomura
142 | CONTROLS & GOVERNANCE | Vendor Controls | Confirm vendor security posture and environment controls | Nomura
143 | CONTROLS & GOVERNANCE | Vendor Controls | Define data retention and deletion policy for vendor environment post-POC | Nomura
144 | ROLE BASED ACCESS CONTROL | RBAC Design | Finalise role taxonomy (Ops Analyst / Team Lead / Manager / Compliance / Read-only) | Nomura
145 | ROLE BASED ACCESS CONTROL | RBAC Design | Define permission matrix — which roles can view, act, approve, admin | Nomura
146 | ROLE BASED ACCESS CONTROL | RBAC Design | Define asset class level access restrictions (OTC vs FX per role) | Nomura
147 | ROLE BASED ACCESS CONTROL | RBAC Design | Review RBAC design with Compliance and Controls | Nomura
148 | ROLE BASED ACCESS CONTROL | RBAC Design | Sign off RBAC design document | Nomura
149 | ROLE BASED ACCESS CONTROL | RBAC Implementation — Vendor | Vendor unit tests all role-permission combinations | Vendor
150 | ROLE BASED ACCESS CONTROL | RBAC Implementation — Vendor | Vendor provides RBAC test evidence / screenshots for Nomura review | Vendor
151 | ROLE BASED ACCESS CONTROL | RBAC UAT | UAT test cases for each role — positive and negative scenarios | Nomura
152 | ROLE BASED ACCESS CONTROL | RBAC UAT | Verify role-based UI element visibility (menus, buttons, data fields) | Nomura
153 | ROLE BASED ACCESS CONTROL | RBAC UAT | Verify unauthorised access is blocked and logged | Nomura
154 | ROLE BASED ACCESS CONTROL | RBAC UAT | Sign off RBAC UAT results | Nomura
155 | INPUT SOURCE INTEGRATION | Email Integration | Define and agree email ingestion spec (mailbox, triggers, parsing rules) | Nomura
156 | INPUT SOURCE INTEGRATION | Email Integration | Integration test: email → AI engine → portal (vendor environment) | Vendor
157 | INPUT SOURCE INTEGRATION | Email Integration | Integration test: email → AI engine → portal (Nomura environment) | Nomura
158 | INPUT SOURCE INTEGRATION | Email Integration | UAT: validate email-triggered case creation with real sample emails | Nomura
159 | INPUT SOURCE INTEGRATION | Email Integration | Sign off email integration | Nomura
160 | INPUT SOURCE INTEGRATION | TRAM Integration | Define and agree TRAM message ingestion spec (message types, fields, routing) | Nomura
161 | INPUT SOURCE INTEGRATION | TRAM Integration | Integration test: TRAM → AI engine → portal (vendor environment) | Vendor
162 | INPUT SOURCE INTEGRATION | TRAM Integration | Integration test: TRAM → AI engine → portal (Nomura environment) | Nomura
163 | INPUT SOURCE INTEGRATION | TRAM Integration | UAT: validate TRAM-triggered case creation with real sample messages | Nomura
164 | INPUT SOURCE INTEGRATION | TRAM Integration | Sign off TRAM integration | Nomura
165 | INPUT SOURCE INTEGRATION | Shared Folder Integration | Define and agree shared folder spec (path, file types, polling interval) | Nomura |  |  | will we have any shared folder integration with vendor from Nomura ?
166 | INPUT SOURCE INTEGRATION | Shared Folder Integration | Integration test: shared folder → AI engine → portal (vendor environment) | Vendor
167 | INPUT SOURCE INTEGRATION | Shared Folder Integration | Integration test: shared folder → AI engine → portal (Nomura environment) | Nomura
168 | INPUT SOURCE INTEGRATION | Shared Folder Integration | UAT: validate shared folder triggered case creation with sample files | Nomura
169 | INPUT SOURCE INTEGRATION | Shared Folder Integration | Sign off shared folder integration | Nomura
170 | TESTING & UAT | Test Planning | Prepare UAT test plan — scope, entry/exit criteria, test environment | Nomura
171 | TESTING & UAT | Test Planning | Prepare test cases for OTC Derivatives use cases for all 3 input sources (email, TRAM, shared folder) | Nomura
172 | TESTING & UAT | Test Planning | Prepare test cases for FX use cases for all 3 input sources (email, TRAM, shared folder) | Nomura
173 | TESTING & UAT | Test Planning | Prepare negative / edge case test scenarios for OTC derivatives & FX usecases | Nomura
174 | TESTING & UAT | Test Planning | Prepare RBAC test cases (all roles, positive and negative) for OTC derivatives & FX usecases | Nomura
175 | TESTING & UAT | Test Planning | Review and sign off test plan for OTC derivatives & FX usecases | Nomura
176 | TESTING & UAT | Test Execution | Execute test cases for OTC Derivatives — Nomura internal environment | Nomura |  |  | This is SIT testing
177 | TESTING & UAT | Test Execution | Log defects and track resolution for OTC cases | Nomura |  |  | This is SIT testing
178 | TESTING & UAT | Test Execution | Execute test cases for FX usecases — Nomura internal environment | Nomura |  |  | This is SIT testing
179 | TESTING & UAT | Test Execution | Log defects and track resolution for FX cases | Nomura |  |  | This is SIT testing
180 | TESTING & UAT | UAT Execution | Define UAT users for OTC derivatives & FX usecases | Nomura | Sandhya |  | UAT is business users testing
181 | TESTING & UAT | UAT Execution — OTC Derivatives | Execute UAT test cases for OTC Derivatives — Nomura internal environment | Nomura
182 | TESTING & UAT | UAT Execution — OTC Derivatives | Log defects and track resolution for OTC cases | Both
183 | TESTING & UAT | UAT Execution — OTC Derivatives | Retest OTC defect fixes | Nomura
184 | TESTING & UAT | UAT Execution — OTC Derivatives | OTC Derivatives UAT sign-off | Nomura
185 | TESTING & UAT | UAT Execution — FX | Execute UAT test cases for FX — vendor environment | Nomura
186 | TESTING & UAT | UAT Execution — FX | Execute UAT test cases for FX — Nomura internal environment | Nomura
187 | TESTING & UAT | UAT Execution — FX | Log defects and track resolution for FX cases | Both
188 | TESTING & UAT | UAT Execution — FX | Retest FX defect fixes | Nomura
189 | TESTING & UAT | UAT Execution — FX | FX UAT sign-off | Nomura
190 | TESTING & UAT | UAT Execution — Input Sources | UAT: end-to-end test via Email input source | Nomura
191 | TESTING & UAT | UAT Execution — Input Sources | UAT: end-to-end test via TRAM input source | Nomura
192 | TESTING & UAT | UAT Execution — Input Sources | UAT: end-to-end test via Shared Folder input source | Nomura
193 | TESTING & UAT | UAT Execution — Input Sources | Validate multi-source case deduplication behaviour | Nomura
194 | TESTING & UAT | UAT Execution — Input Sources | Input source integration UAT sign-off | Nomura
195 | TESTING & UAT | UAT Execution — RBAC | UAT: validate each user role in vendor portal | Nomura
196 | TESTING & UAT | UAT Execution — RBAC | UAT: validate each user role in Nomura internal portal | Nomura
197 | TESTING & UAT | UAT Execution — RBAC | Validate audit logs capture user actions per role | Nomura
198 | TESTING & UAT | UAT Execution — RBAC | RBAC UAT sign-off | Nomura
199 | TESTING & UAT | Defect Management | Set up defect tracking log (shared between Nomura and Vendor) | Both
200 | TESTING & UAT | Defect Management | Triage defects — classify as Critical / Major / Minor | Both
201 | TESTING & UAT | Defect Management | Vendor fixes all defects | Vendor
202 | TESTING & UAT | Defect Management | Final defect closure review and sign-off | Nomura
203 | TESTING & UAT | UAT Sign-off | Compile UAT completion report (coverage, pass rate, open defects) | Nomura
204 | TESTING & UAT | UAT Sign-off | Business sign-off on UAT completion — OTC and FX | Nomura
205 | TESTING & UAT | UAT Sign-off | Operations team sign-off on portal usability | Nomura
206 | TESTING & UAT | UAT Sign-off | Controls and Compliance sign-off on RBAC and audit trail | Nomura
207 | GO-LIVE & POST GO-LIVE | Go-live Readiness | Confirm all UAT sign-offs obtained | Nomura
208 | GO-LIVE & POST GO-LIVE | Go-live Readiness | Confirm NTI , automation registry id and governance approvals in place for go-live | Nomura
209 | GO-LIVE & POST GO-LIVE | Go-live Readiness | Confirm RBAC provisioned for all live users | Both
210 | GO-LIVE & POST GO-LIVE | Go-live Readiness | Confirm all 3 input source connectors live and validated | Both
211 | GO-LIVE & POST GO-LIVE | Go-live Readiness | Go / No-Go decision meeting with stakeholders | Nomura
212 | GO-LIVE & POST GO-LIVE | POC Go-live — Nomura Environment | Deploy POC in Nomura internal environment | Nomura
213 | GO-LIVE & POST GO-LIVE | POC Go-live — Nomura Environment | Smoke test all use cases in Nomura environment (OTC + FX) | Nomura
214 | GO-LIVE & POST GO-LIVE | POC Go-live — Nomura Environment | Smoke test all input sources in Nomura environment | Nomura
215 | GO-LIVE & POST GO-LIVE | POC Go-live — Nomura Environment | Confirm RBAC working in Nomura live environment | Nomura
216 | GO-LIVE & POST GO-LIVE | Hypercare | Hypercare period — daily monitoring of AI accuracy and exception resolution | Both
217 | GO-LIVE & POST GO-LIVE | Hypercare | Track false positive / false negative rate during hypercare | Nomura
218 | GO-LIVE & POST GO-LIVE | Hypercare | Log operational issues during hypercare and assign to vendor or Nomura | Both
219 | GO-LIVE & POST GO-LIVE | Hypercare | Weekly hypercare review meeting (Nomura + Vendor) | Both
220 | GO-LIVE & POST GO-LIVE | Hypercare | Hypercare exit criteria review and sign-off | Nomura
221 | GO-LIVE & POST GO-LIVE | POC Review & Evaluation | Compile POC outcomes report (accuracy, throughput, user feedback) | Nomura
222 | GO-LIVE & POST GO-LIVE | POC Review & Evaluation | Stakeholder presentation of POC results to senior management | Nomura
223 | GO-LIVE & POST GO-LIVE | POC Review & Evaluation | Decision: proceed to production / scale / pivot | Nomura
224 | DECOMMISSION / HANDOVER | Knowledge Transfer | Vendor to deliver full technical documentation of POC build | Vendor
225 | DECOMMISSION / HANDOVER | Knowledge Transfer | Vendor to conduct knowledge transfer sessions with Nomura dev team | Both |  |  | will we tak KT? As we are not sure if the same vendor will deploy for other usecases?
226 | DECOMMISSION / HANDOVER | Knowledge Transfer | Nomura team to document Nomura internal build decisions and learnings | Nomura
227 | DECOMMISSION / HANDOVER | Knowledge Transfer | Consolidate all documentation in Nomura knowledge repository | Nomura
228 | DECOMMISSION / HANDOVER | Vendor Environment Closedown | Confirm deletion of all Nomura data from vendor environment post-POC | Vendor
229 | DECOMMISSION / HANDOVER | Vendor Environment Closedown | Vendor to provide data deletion certificate | Vendor
230 | DECOMMISSION / HANDOVER | Vendor Environment Closedown | Revoke Nomura access to vendor environment | Both
231 | DECOMMISSION / HANDOVER | Vendor Environment Closedown | Close vendor NTI and access approvals | Nomura
232 | DECOMMISSION / HANDOVER | Production Readiness Planning | Define requirements delta between POC and production | Nomura
233 | DECOMMISSION / HANDOVER | Production Readiness Planning | Identify production infrastructure requirements (Nomura / Chinou) | Nomura
234 | DECOMMISSION / HANDOVER | Production Readiness Planning | Prepare high level production project plan and effort estimate | Both
235 | DECOMMISSION / HANDOVER | Production Readiness Planning | Present production readiness plan to senior management | Nomura
236 | DECOMMISSION / HANDOVER |  | Any applications getting decommissioned , to be checked with business | Nomura